# Dissertation Log

Topic	Covid and Electricity consumption
Name	Krishna Kunjumon
Matriculation ID	40478289
Supervisor	Stefano Cherubin

Date	Meeting	Deadline	Task	Comment
04/06/2021	M		M: Discussed on topic and work to be done. Latex, Github. Template, Bibtex, Data
05/06/2021			Went through the topics discussed. / Setup Template – Overleaf / Setup Github Repository	Setup succesfully
06/06/2021
07/06/2021
08/06/2021			Preparing alternate plans	3 plans set out: / Plan A: Research with hospital data / Plan B: Commercial building data / Plan C: General data with new point of interest.
09/06/2021
10/06/2021
11/06/2021	M		Discussed on developing new alternate plans
12/06/2021			Search for data on hospitals- random search	Hospital data unavailable
13/06/2021			Search for data on hospitals – wrt previous researches	All data from hospitals directly. No data available as open source.
14/06/2021			Search for commercial building data	No recent data available. Research papers referred site for data identified, but data is not current.
15/06/2021			Search for alternate plan data – general data	General data available, but scattered with respect to country, weather
16/06/2021			Search for general data, Developing new point of interest in research, literature review
17/06/2021			Gathering required data, Developing new point of interest in research, literature review	Identified different data sources. Carried out literature review
18/06/2021	M		Discussed Development on alternate plan
19/06/2021			Gathered data
20/06/2021			Gathered data, identifying the best suitable ones to be used in research.	Decided on proceeding with Ontario dataset. Latest Load, weather, mobility data readily available.
21/06/2021			Pre-processing data: Combining data: combining last 4 years load, weather, 2-year mobility data from different sources into a single file based on the date on the data.	Successfully created a data frame with all the necessary data combined.
22/06/2021			Literature review on usage of mobility data. Started performing time series analysis
23/06/2021			Time series analysis, / Data Cleaning-Correcting tables, column names, missing values, / Updating github
24/06/2021			Intial report, Framing research question
25/06/2021	M		Worked on research question, Came across hospital data, but could not be used due to lack of energy data of hospitals.
26/06/2021			Focussed on smart grid, studying the impact of covid on the resilience and flexibility of grid to identify the scope of ML and its implementation.
27/06/2021
28/06/2021
29/06/2021			Developed a research question and aim.
30/06/2021			Preparing intial report and Research proposal.	Prepared research question and initial report
01/07/2021
02/07/2021	M
03/07/2021
04/07/2021		1.Framing Research Question. / 2.Initial report Modification / 3.EDA
05/07/2021
06/07/2021
07/07/2021
08/07/2021
09/07/2021	M			Shared initial report and plan research question updated.
10/07/2021
11/07/2021		Assessing Flexibility: ML Approach
12/07/2021
13/07/2021
14/07/2021
15/07/2021
16/07/2021	M
17/07/2021
18/07/2021		Assessing Flexibility: ML Approach
19/07/2021
20/07/2021
21/07/2021
22/07/2021
23/07/2021	M
24/07/2021
25/07/2021		Model Evaluation
26/07/2021			Refreshing the work done so far.
27/07/2021			Visualising data
28/07/2021			EDA techniques
29/07/2021
30/07/2021	M
31/07/2021
01/08/2021		Results and Finding
02/08/2021
03/08/2021
04/08/2021
05/08/2021
06/08/2021	M
07/08/2021
08/08/2021		Smart grid Review
09/08/2021
10/08/2021
11/08/2021
12/08/2021
13/08/2021	M
14/08/2021
15/08/2021		Documentation
16/08/2021
17/08/2021
18/08/2021

## Weekly Update and Meeting insight:
04/06/2021	Had the first meeting with supervisor. Shared the proposal and initial report for reference. Discussed on the topic and challenges to be addressed. Data for research is a major challenge. Discussed on finding data. If not alterative approaches that could be made on the data. Discussed about the writing- should be more of critical than descriptive. Discussed on template for dissertation, Glossary, Bibtex, Latex, github etc.
11/06/2021	Setup template, github repository. Data not found. Alternate plans made. Focussed on finding suitable dataset for research. Developed alternative approaches
18/06/2021	Alternate plans discussed. Started on finding suitable dataset.
25/06/2021

Project Plan:
Data Mining:
Business Understanding:
Project Goal and requirements
Determine business Objective: project target, what customer wants to achieve, factors effecting result.
Access Situation: detailed analysis of facts, resources, constrains, assumptions.
Determine data mining goals:
Produce a project plan: expected steps to perform.

1. Data understanding
2. Dta Preparation
3. Modelling
4. Evaluation
5. Deployment